## Sheet1
Week | CI-CD pipeline project
2023-02-01 | Project Planning | Estimated Houres | Weekly plan
2023-02-08 | Creat Github repo | 4 | 1-Creat repo 2-Uoload project files 2-Creat make file 3-Creat requirement.txt
2023-02-15 | Set up clous shell enviroment | 4 | 1- creat python virtual enviroment 2-Creat project scrypt test file and test file
2020-02-22 | Enable Github Actions | 2 | Verify Remote Tests pass
2/29/2023 | Authorize Azure app service | 4 | 1- Upload flask files to the repo 2-creat Azure web app
2023-03-05 | Enable continous diploiment with azure pipeline | 4 | 1-integrate CI 2-integrate CD
2023-03-12 | Deploy Flask ML | 2 | 1-deploy initial version
2023-03-19 | New featur | TBD | TBD
2023-03-26 | Get feed back and develop the app | TBD | TBD
2023-04-03
2023-04-10
2023-04-17
| Goals |  | Goals
Python-based machine learning application using the Flask web framework
performing both Continuous Integration and Continuous Delivery